COMPANION DOCUMENT  ·  WORKING DOCUMENT

Prepared for SX Collective

Project Timeline & Scope

This document accompanies the signed engagement letter and covers the weekly phases, working session cadence, deliverable milestones, and dependencies for the project. Each tier runs on its own length (30, 60, or 90 days), and the structure below scales to the tier selected in the engagement letter. Dates are anchored to the confirmed kickoff, and the document is updated together during the engagement if inputs, data, or priorities change.

Important. This is a working document, not a contract. It is illustrative of the work produced during the engagement and evolves as Consultant and Client learn more together. Specific formats, granularity, quantities, styles, brands, timelines, and metrics referenced in this document are subject to change based on the data available, input from the people involved, and priorities that emerge during the engagement. This document does not modify or expand the commercial terms in the signed proposal or the Master Services Agreement. Neither party is legally bound to any specific content, format, quantity, or outcome described here. The proposal and the signed engagement letter govern the engagement; this document supports it.

Confirmed kickoff date	Week of  ____________________

Final walk-through date	30, 60, or 90 days from kickoff (varies by tier)

Selected tier	____________________________________

01 · Engagement Shape

The project arc.

The engagement moves through four phases plus a final walk-through, with structured working sessions built in to test thinking against the data before it becomes a deliverable. The phase shape is the same across tiers. What scales is the length of each phase and the depth of the work, both of which match the tier selected in the engagement letter.

Workflow at a glance

Phases shown proportionally. Each phase scales to the project length of the tier selected. Tier 01: roughly one week per phase. Tier 02: roughly two weeks per phase. Tier 03: roughly three weeks per phase. Calendar dates are confirmed at engagement letter signature.

| Phase | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Walk-through |
| --- | --- | --- | --- | --- | --- |
| Kickoff |  |  |  |  |  |
| Discovery |  |  |  |  |  |
| Diagnosis |  |  |  |  |  |
| Build the plan |  |  |  |  |  |
| Working sessions |  |  |  |  |  |
| Final deliverables |  |  |  |  |  |
| Final walk-through |  |  |  |  |  |

Light bars mark active work. Black bars mark the kickoff and the final walk-through milestones.

Phases by tier

The four phases below sit at the same proportional spots in every project. What changes is the length of each phase. Tier 01 compresses each phase to roughly one week. Tier 02 runs each phase across roughly two weeks. Tier 03 stretches each phase across roughly three weeks. Specific week numbers are agreed at engagement letter signature based on the kickoff date.

| Phase / weeks | Theme | What happens |
| --- | --- | --- |
| Phase 1 T1: Wk 01 · T2: Wks 01–02 · T3: Wks 01–03 | Discovery & alignment | Kickoff call. Team conversations with 2 to 5 people on the client side. Document review of current brand roster, financials, and any existing store or concept thinking. Confirm success metrics and decision rights for the engagement. |
| Phase 2 T1: Wk 02 · T2: Wks 03–04 · T3: Wks 04–06 | Diagnosis & framing | Assortment audit, competitive scan of adjacent retail concepts, margin and unit economics review on representative products. Working Session 1 with the client to align on findings before any recommendations are committed. |
| Phase 3 T1: Wk 03 · T2: Wks 05–06 · T3: Wks 07–09 | Build the plan | Pull findings together into the assortment framework (all tiers). Tier 03 also develops the retail concept positioning and the marketing and assortment tie-in framework. Working Session 2 to check the strategy with the client (Tiers 02 and 03). |
| Phase 4 T1: Wk 04 · T2: Wks 07–08 · T3: Wks 10–12 | Land the plan | Final deliverables packaged. Pre-read of final deliverables shared. Client review window opens on deliverable delivery and closes five business days later per Deliverable Acceptance terms. Training handoff begins for the day to day owner. |
| Walk-through T1: Wk 05 · T2: Wk 09 · T3: Wk 13 | Final walk-through | Final walk-through delivered, decisions captured, and next steps framed. Final invoice issued. Training handoff wraps so the team can continue execution after the engagement closes. |

Working session cadence

Working sessions are 60 to 75 minute calls designed to land decisions, not just have a discussion. Each one has a pre-read sent 24 to 48 hours ahead and a short decisions and open questions summary sent within 24 to 48 hours after. Specific week placement scales to the selected tier.

- Kickoff. 60 to 75 min. Success metrics, decision rights, data access checklist, team conversations schedule. All tiers.

- Working Session 1. 60 min. Diagnosis and findings alignment, held during Phase 2. All tiers.

- Working Session 2. 60 min. Strategy framework review, held during Phase 3. Tiers 02 and 03.

- Working Session 3. 60 min. Retail concept and marketing frameworks review, held during Phase 3. Tier 03 only.

- Final pre-read. 30 min. Walk-through of the final deliverable draft before the final walk-through, to surface any last adjustments. Held during Phase 4. Tiers 02 and 03.

- Final walk-through. 60 to 90 min. Final deliverable walk-through, decisions captured, next steps framing. All tiers.

02 · Deliverable Milestones

What lands when.

Milestones are anchored to the confirmed kickoff date. Day numbers are relative to kickoff (Day 1) and scale to the tier selected. Tier 01 lands on a 30-day arc, Tier 02 on a 60-day arc, and Tier 03 on a 90-day arc. Specific calendar dates are filled in at engagement letter signature.

| Milestone | Tier 01 day | Tier 02 day | Tier 03 day | Applies to |
| --- | --- | --- | --- | --- |
| Engagement letter and NDA countersigned. Deposit invoice issued. | Day -7 | Day -7 | Day -7 | All tiers |
| Kickoff pre-read sent. Data access checklist shared. | Day -2 | Day -2 | Day -2 | All tiers |
| Kickoff call. Success metrics and decision rights confirmed. | Day 1 | Day 1 | Day 1 | All tiers |
| Team conversations complete. Document review wrapped. | Day 5 | Day 10 | Day 14 | All tiers |
| Working Session 1. Diagnosis and findings alignment. | Day 9 | Day 17 | Day 26 | All tiers |
| Diagnostic findings draft delivered for review. | Day 12 | Day 24 | Day 36 | All tiers |
| Working Session 2. Strategy framework review. | — | Day 33 | Day 50 | Tiers 02 + 03 |
| Working Session 3. Retail concept and marketing review. | — | — | Day 58 | Tier 03 only |
| Strategic plan draft delivered. Client review window opens. | — | Day 45 | Day 68 | Tiers 02 + 03 |
| 30-min final deliverables preview call. | — | Day 50 | Day 75 | Tiers 02 + 03 |
| Client review window closes. Final revisions incorporated. | Day 22 | Day 53 | Day 80 | All tiers |
| Training handoff call with the day to day owner. | — | Day 57 | Day 85 | Tiers 02 + 03 |
| Final walk-through. Deliverables delivered. Final invoice issued. | Day 30 | Day 60 | Day 90 | All tiers |

Milestones are the operating rhythm. Any change to a delivery date is flagged in writing at least five business days in advance and agreed collaboratively.

03 · Scope by Tier

What the deliverables actually contain.

This section expands the deliverables listed in the proposal. It describes the specific contents and scope of each output so both parties are aligned on what the work actually looks like. This document is the operational reference, not a contract.

Tier 01: The Diagnostic

- Review of current assortment, brand roster, and MAP policy direction. Intended to flag gaps, overlaps, and consolidation candidates at the style or product group level. (SKU-level analysis to optimize size curves by brand for the highest margin and conversion is a follow-on scope, typically on retainer.)

- Margin and unit economics review of the assortment. Estimated coverage of 3 to 5 representative styles with flagged pricing or brand mix anomalies and directional margin impact of each. Exact scope is a goal, not a fixed commitment.

- Competitive scan of 3 to 4 adjacent retail concepts across specialty run, outdoor, and lifestyle. Output is a short positioning view showing where SX sits relative to each.

- Ranked opportunity list, usually 5 to 7 items, prioritized by speed to revenue or margin, with a directional impact estimate (in dollars, points, or percent as appropriate) and a rough read on effort to execute.

- Written diagnostic document with findings, risks, and the ranked list. Underlying analysis is shared as a companion spreadsheet.

- Up to 3 team conversations with the people closest to the work.

- 60-minute final walk-through with findings walk-through and decisions captured.

- Up to 3 rounds of revision on the written diagnostic.

Tier 02: The Assortment Plan

- Everything in Tier 01.

- 12-month assortment plan. Intended to include style level or category level targets, brand allocation percentages by category, and margin targets by category. Final format and granularity are agreed together during the engagement based on the data available.

- Brand roster framework using Build / Maintain / Test / Exit categories, with brand assignments and the reasoning behind each placement.

- MAP policy and pricing recommendations covering pricing floors, promo windows, and enforcement triggers at the style or category level.

- Directional notes on retail concept (Pillar 02) and marketing tie-ins (Pillar 03). Usually 2 to 3 next step recommendations for each. Not full plans at this tier.

- 60 / 90 / 120 day execution plan focused on Pillar 01, with suggested owners, decision points, and target revenue or margin outcomes at each milestone. Suggested owners are starting points. The client distributes work across the team as they see fit.

- Up to 5 team conversations with the people closest to the work.

- 2 mid-engagement working sessions, a 30-minute final deliverables preview in Week 08, and a final walk-through deck delivered in Week 09.

- Up to 3 rounds of revision on each deliverable.

Tier 03: The Full Plan

- Everything in Tier 02.

- Retail concept positioning document. Intended to cover community model specifics, store format requirements (size, layout, fixture types, and prototype store or sample sale mechanics), and an activation calendar tied to run club events and athlete moments.

- Marketing and assortment tie-in framework. Usually includes 3 to 5 campaign concepts tied to product drops or run club events, each with target audience, channel mix, and a success metric. Built to work without paid media, with the option to collaborate with the client's paid media specialist and their existing paid plan if one is in place.

- Content and events calendar (roughly 90 days) connecting drops to the underlying assortment.

- Vendor outreach starter list for 3 to 5 forward looking brands beyond the roster covered in the proposal (for example Satisfy, District Vision, Speedland, Hylo, Mount to Coast, or others agreed at kickoff). Contacts I have on hand are included; for brands I don't know directly, I'll do the research and ask for referrals from reps I've worked with before. Actively pursuing these brands beyond the initial outreach is a retainer scope activity, or can be handed off to someone on the client's side if the project ends here.

- 60 / 90 / 120 day execution plan across all three pillars, with suggested owners, decision points, and target revenue or margin outcomes at each milestone. Suggested owners are starting points. The client distributes work across the team as they see fit.

- Up to 7 team conversations with the people closest to the work.

- 3 mid-engagement working sessions, a 30-minute final deliverables preview in Week 08, and a final walk-through deck delivered in Week 09.

- Up to 3 rounds of revision on each deliverable.

Final format, granularity, and exact contents of each deliverable are agreed together during the engagement and reflected in this document, not in the proposal. The goal is to match the depth of the output to the depth of the data available and the decisions the work needs to support.

04 · Dependencies & Inputs

What keeps the plan on track.

The timeline above assumes the following inputs and access are provided by the client on the schedule indicated. Delays on any of these shift downstream milestones. See the Stop-work clause in the proposal terms.

From the client, by end of Week 01

- A single point of contact for scheduling, introductions, and data access

- Editable CSV or Excel exports of current assortment data (style list, cost, sell-through, inventory on hand) within Week 01. Files can carry whatever password protection, watermarking, NDA scope, or other access controls the client needs. None of it leaves this engagement, per the Confidentiality clause.

- Current P&L or unit economics reference (even rough) to support the margin and unit economics review. I'm able to work with a multitude of financial metrics (P&L, project budget, OTB, etc.) and will report against whichever ones the client prefers.

- Intros to the 2 to 5 people identified at kickoff beyond Hunter (my direct contact and founder). The ones you want me to learn from, the ones who will have the biggest impact on results, and the ones who will be trained to run the day to day after the project closes.

- Any existing brand, concept, or investor documents that describe the SX Collective vision

Ongoing, throughout the engagement

- Feedback on drafts within 3 business days of delivery

- Availability for the scheduled working sessions (1 / 2 / 3 mid-engagement sessions depending on tier, plus final pre-read for Tiers 02 and 03)

- A decision maker available within 48 to 72 hours for escalations on scope or direction

From the consultant

- Responsiveness within one business day, Monday through Friday, during the engagement

- Written check-ins at key milestones summarizing progress, open questions, and what's needed from the client next. Cadence is set at kickoff, not fixed to a weekly calendar.

- Pre-reads delivered 24 to 48 hours before every working session

- Decisions and open questions summary within 24 to 48 hours of every working session

Changes to this document are captured in the change log below. Both parties reference this document, together with the signed engagement letter, as the working scope of the project.

05 · Change Log

Document history.

Each material update to this document is logged below. Entries are added during the engagement as scope, format, granularity, or timing change. The most recent version sits at the top.

| Date | Version | Change | Logged by |
| --- | --- | --- | --- |
| __________ | v1.0 | Initial document shared alongside signed engagement letter. | Consultant |
| __________ | __________ | ____________________________________________________________ | __________________________ |
| __________ | __________ | ____________________________________________________________ | __________________________ |
| __________ | __________ | ____________________________________________________________ | __________________________ |
| __________ | __________ | ____________________________________________________________ | __________________________ |
| __________ | __________ | ____________________________________________________________ | __________________________ |
| __________ | __________ | ____________________________________________________________ | __________________________ |
| __________ | __________ | ____________________________________________________________ | __________________________ |

How changes are made: either party can request a change in writing. The other party reviews within two business days, and either approves the change, asks for clarification, or declines. Approved changes are logged here with date, version, summary, and who logged the change. The change does not modify the commercial terms in the signed proposal or the Master Services Agreement.

OPPORTUNITY DESIGNED

Strategy that holds.  ·  Where rigor meets range.