PROPOSAL · APRIL 2026

Prepared for

SX Collective

A 30-day project to tighten the assortment, sharpen the retail concept, and find the fastest path to revenue.

| Proposed kickoff | Week of ____________________ |
| --- | --- |
| Final readout | 30 days from kickoff |
| Proposal valid through | 30 days from issue date |

| From | The Strategy Studio |
| --- | --- |
| Author | Addie Morrow |
| Contact | adelitamorrow@gmail.com · 385.471.7867 |

01 · The Opportunity

What we heard.

SX Collective is building something the specialty retail world doesn't currently have. A curated outdoor and run concept built around the store as the influencer, the assortment as a point of view, and the community as the marketing engine. The brand roster is sharp. The retail philosophy is real. The work ahead is to turn the vision into something that actually works when customers walk through the door, vendors pick up the phone, and the first buy lands.

Three things stood out from the working notes:

- A defined assortment philosophy across snow, hike, trail, road, and water, anchored by core brands and lifted by trend-forward names like Satisfy, District Vision, Speedland, Hylo, and Mount to Coast.

- A retail model that pushes back on the influencer approach in favor of athlete experts, run club integration, and a prototype-store-as-tradeshow format.

- Real open questions about COGS, margin architecture, warehouse logistics, and what "fastest ROI" actually looks like across e-comm and physical.

This proposal is built around closing those open questions in 30 days and giving you a real plan for what to build, buy, and launch first. I'll work closely with you and your team the whole way. We'll make the hard calls together in Week 01 and keep making them together until the final readout.

02 · The Approach

Three pillars. One 30-day engagement.

Every option below is built on the same three pillars we talked through. What changes between tiers is how deep we go, what you walk away with, and how much of the work we actually do inside the 30 days.

Pillar 01: Assortment & brand roster

A clear view of what SX Collective sells, why, and in what mix. Test brand selection against margin, MAP integrity, and the trend-vs-core balance. Call out which brands are buy-now, which are build-toward, and which are noise.

Pillar 02: Retail concept & community model

Turn the anti-influencer, athlete-led, run-club-anchored philosophy into a real store concept and activation plan, including the prototype-store / tradeshow-to-the-public format and how it plugs into the space you already have.

Pillar 03: Marketing tie-ins & fastest-ROI initiatives

Sequence the work so e-comm wins fund the physical experience. Find the marketing-to-assortment moments that move product without spending into an advertising budget that doesn't fit the brand.

03 · Engagement Options

Three ways to work together.

All three options run for the same 30 days. They differ in how much of the three-pillar work gets built, how many people we pull in, and how deep we go on the final deliverables.

|  | Tier 01 | Tier 02 Recommended | Tier 03 |
| --- | --- | --- | --- |
|  | The Diagnostic | The Assortment Plan | The Full Plan |
| Investment | $6,000 | $9,500 | $15,000 |
| Duration | 30 days | 30 days | 30 days |
| Engagement style | Fixed scope, deliverable-based | Fixed scope, deliverable-based | Fixed scope, deliverable-based |
| Pillar coverage | Pillar 01 only (assessed) | Pillar 01 deep. Pillars 02 and 03 directional. | All three pillars at full strategic depth |
| Best for | You want an outside read before committing to a full plan. | You want to lock in the assortment and brand roster first, then tackle store and marketing next. | You want one engagement that delivers the whole operating plan end-to-end. |
| Working sessions | 1 kickoff + 1 working + 1 readout | 1 kickoff + 2 working + 30-min final pre-read + 1 readout | 1 kickoff + 3 working + 30-min final pre-read + 1 readout |
| Stakeholder interviews | Up to 3 | Up to 5 | Up to 7 |
| Final deliverables | Diagnostic report + prioritized opportunity list | Everything in Tier 01 + 12-month assortment plan + brand roster framework + directional notes on retail concept and marketing | Everything in Tier 02 + full retail concept positioning + marketing-to-assortment framework + vendor outreach starter list |

If you're early and watching your cash, Tier 02 is the right move. It locks in the most important decision, which is assortment, without overinvesting before the retail concept is tested with real customers. Most of the margin in specialty retail is made or lost in the first 90 days of the buy. Get that right, and everything downstream gets easier. The retail concept and marketing work becomes a clear next step once the foundation is set.

04 · What's Included

Scope by tier.

Tier 01: The Diagnostic

$6,000

30-day engagement  ·  Fixed-scope, deliverable-based

An outside read on the assortment and brand roster. You walk away with a written diagnostic, a view of where the revenue and margin risks sit, and a ranked list of moves to make first.

- Review of the current assortment, brand roster, and MAP policy direction

- Margin and unit-economics review of the assortment

- Competitive scan of adjacent retail concepts

- Ranked opportunity list prioritized by speed to revenue or margin

- Written diagnostic with findings, risks, and recommendations

- Up to 3 stakeholder interviews

- Executive readout

- Specific contents and scope of each deliverable are detailed in the accompanying Project Timeline & Scope document

What you get out of it: A clearer read on where the revenue and margin risks are and a ranked list of the first moves to make.

Tier 02: The Assortment Plan

$9,500    Recommended

30-day engagement  ·  Fixed-scope, deliverable-based

Everything in The Diagnostic, plus a strategic plan for Pillar 01 (assortment and brand roster) and directional pointers on Pillars 02 and 03. You leave with an assortment plan you can work from for the next 12 months.

- Everything included in Tier 01

- 12-month assortment plan

- Brand roster framework

- MAP policy and pricing recommendations for the assortment

- Directional notes on retail concept and marketing tie-ins (not full plans at this tier)

- 30 / 60 / 90 day execution plan focused on Pillar 01

- Up to 5 stakeholder interviews

- 2 mid-engagement working sessions, a final-deliverables pre-read in Week 04, and a final readout

- Specific contents and scope of each deliverable are detailed in the accompanying Project Timeline & Scope document

What you get out of it: A buying and brand roster plan you can work from for the next 12 months, with the thinking behind it written down so you can share it with whoever needs to see it.

Tier 03: The Full Plan

$15,000

30-day engagement  ·  Fixed-scope, deliverable-based

Everything in The Assortment Plan, plus strategic plans for Pillars 02 and 03. You leave with a plan that covers assortment, retail concept, and marketing together, with vendor and community work already in motion.

- Everything included in Tier 02

- Retail concept positioning

- Marketing-to-assortment tie-in framework

- Vendor outreach starter list for trend-opportunity brands

- 30 / 60 / 90 day execution plan across all three pillars

- Up to 7 stakeholder interviews

- 3 mid-engagement working sessions, a final-deliverables pre-read in Week 04, and a final readout

- Specific contents and scope of each deliverable are detailed in the accompanying Project Timeline & Scope document

What you get out of it: A plan that covers assortment, retail concept, and marketing as one piece, with early vendor and community work already in motion by the end of the 30 days.

05 · Why Me

Why I'm the right person for this.

You're hiring someone to help make real buying, margin, and brand decisions for SX Collective. Here's what I bring to those conversations.

- I've actually done this job. 10+ years buying and running merchandise strategy at Backcountry (footwear across Nike, Adidas Terrex, Merrell, Salomon, Norda, Brooks, On Running, and others) and as Director of Purchasing at New World Natural Brands. Every recommendation I'll give you has been carried out under a real P&L. I know what it feels like to own the number, because I've owned it.

- I know the brands you care about. Satisfy, District Vision, Speedland, Hylo, Mount to Coast, and the core roster around them are not abstract to me. I've bought adjacent brands, know the vendor reps, and can talk about margin, positioning, and sell-through without needing to do weeks of research first.

- I live in the world SX is building for. I run, ski, and spend my weekends in the same community you're designing around. The athlete-expert, anti-influencer positioning is not something I have to study. It's how I already think about product, people, and stores.

- I'm in it with you. This isn't a consulting gig where I hand you a deck and walk away. I want to help you actually build this, which means I'll push back when I disagree, sit next to you in the hard calls, and tell you the real answer when it matters more than the pretty one.

06 · Timeline

A companion document.

A detailed Project Timeline & Scope document covering weekly phases, working sessions, deliverable milestones, and dependency mapping is shared alongside the signed engagement letter once a kickoff date is confirmed. That document becomes the operating reference for the 30 days and is updated collaboratively if inputs or priorities shift.

Committing to the shape of the work here, and to the specifics of the schedule in the companion document, keeps this proposal focused on terms and gives us room to adapt the plan as we learn more about the data.

07 · What We Need From You

To keep the 30 days on track.

The work moves as fast as I can get the information I need. Here's what I'll be asking you for to keep the 30 days on track.

- A single point of contact for scheduling, introductions, and data access

- Editable CSV or Excel exports of current assortment data (SKU list, cost, sell-through, inventory on hand) within Week 01. Files can carry whatever password protection, watermarking, NDA scope, or other access controls you need. I need editable formats to sort, pivot, and actually work the data. None of it leaves this engagement, per the Confidentiality clause.

- Current P&L or unit-economics reference (even rough) to support the margin and unit-economics review

- Intros to 2 to 5 people on your side (founder, operator, data/ecomm lead, including Hunter for the data cut)

- Any existing brand, concept, or investor documents that describe the SX Collective vision in your own words

- Feedback on drafts within three business days of delivery. Each deliverable includes up to three rounds of revision, and delays beyond the three-day window shift downstream milestones, with timeline adjustments captured in writing.

- Willingness to co-define success metrics at kickoff. We'll agree in Week 01 on the two or three outcomes that matter for you to call this engagement a success.

Kickoff preview

The Week 01 kickoff call runs 60 to 75 minutes and covers: (1) the top three questions SX needs answered by the end of the 30 days, (2) what success looks like to you, in your words, (3) a quick walk-through of the data access checklist and who I'll be interviewing, and (4) who signs off on what, and when. A short pre-read lands in your inbox three business days before the call.

08 · Investment & Terms

The money part.

Pricing is fixed per tier. Payment timing and structure is something we work out together and put in the engagement letter.

| Payment structure | Fixed fee by tier. A non-refundable deposit is required at signed engagement letter, before any work begins. The remainder is paid on agreed milestones. Ideal terms for this first engagement: non-refundable deposit at signature, with the remaining balance payable Net 90 or Net 120 against the final invoice. Offered as a one-time courtesy to support SX Collective's early-stage cash flow. All payment terms, deposit amount, and milestone structure are finalized through negotiation and documented in the signed engagement letter. |
| --- | --- |
| Deposit | Non-refundable. Retained in full if the engagement is terminated for any reason by either party. |
| Revisions | Up to three (3) rounds of revisions per deliverable, requested in writing during the 7-business-day Deliverable Acceptance window. |
| Deliverable acceptance | Deliverables are accepted seven (7) business days after delivery unless Client provides written notice of specific, scope-based objections within that window. Subjective dissatisfaction or strategic disagreement with recommendations is not a valid basis for withholding payment. |
| Termination | Termination before the final readout requires a signed Separation Agreement executed by both parties. The template form is provided as a companion document with this proposal. The deposit is retained in full, no fees are pro-rated, and issued invoices remain payable per their original terms. |
| Confidentiality & IP | Mutual NDA executed before kickoff. All final deliverables owned by Client. Consultant retains rights to frameworks and anonymized learnings for future work. |
| Proposal validity | Pricing and scope above are valid for 30 days from the proposal issue date. |
| Full terms | Late-payment interest, non-payment enforcement, scope flexibility and expansion handling, exclusivity, travel and expenses, liability caps, force majeure, governing law, and all other standard legal provisions are set out in the Master Services Agreement, which is executed alongside this signed proposal before kickoff. |

09 · Next Steps

How we get started.

Three things between this proposal and a kickoff:

- Pick a tier, or tell me what you'd want to flex. Tier 02 (The Assortment Plan) is the recommended starting point.

- Sign the engagement letter and mutual NDA (sent within 24 hours of your selection). The Project Timeline & Scope document is shared at the same time.

- Confirm a kickoff date and the two to five stakeholders we'll interview in Week 01.

After the 30 days: suggested follow-up

The first 30 days covers the hardest part of the work. We set up the assortment framework, build out the retail concept, and tie the marketing to the product calendar. Keeping that moving afterward is better as a monthly rhythm than another one-off project.

What I'd suggest is a monthly retainer starting the month after the final readout, sized based on what the work actually needs to keep moving. Three retainer shapes are available, from light-touch advisory to near-embedded operator, scaled by monthly hours and how involved I am.

A separate Retainer Proposal document is attached and lays out the three shapes, the monthly hours and overage structure, and how we land on the monthly investment. The right fit is something we decide together at the final readout, once we both see what the work really calls for.

A note on first projects

This is the kind of work I built The Strategy Studio for, and I'd love to do this one with you. As with any new business, there are things like vendor responsiveness, internal data access, and scheduling that can occasionally shift a deliverable date by a few days. Where that happens, I'll flag it early and we'll figure out the fix together. Any change to the final readout date needs explicit sign-off from both of us.

10 · Acceptance

Let's get started.

Countersigning below means you're in for the tier selected and the terms in this proposal. A short Master Services Agreement covering the standard legal language, the mutual NDA, and the Separation Agreement template are sent for signature within 24 hours of countersignature. The deposit invoice follows on signed MSA, with the amount and payment terms we worked out together.

| TIER SELECTION |  |
| --- | --- |
| ☐ | Tier 01: The Diagnostic. $6,000. |
| ☐ | Tier 02: The Assortment Plan. $9,500. Recommended. |
| ☐ | Tier 03: The Full Plan. $15,000. |

| FOR SX COLLECTIVE |  | FOR THE STRATEGY STUDIO |
| --- | --- | --- |
| Signature |  | Signature · Addie Morrow |
| Printed name |  | Date |
| Title |  |  |
| Date |  |  |

THE STRATEGY STUDIO

Strategy that holds.  ·  Where rigor meets range.