PROPOSAL · APRIL 2026

Prepared for

SX Collective

A 30-day engagement to pressure-test the assortment, sharpen the retail concept, and identify the fastest path to revenue.

FromThe Strategy Studio

AuthorAddie Morrow

Contactadelitamorrow@gmail.com  ·  385.471.7867

01 · THE OPPORTUNITY

What we heard.

SX Collective is building something the specialty retail world doesn't currently have — a curated outdoor and run concept that treats the store as the influencer, the assortment as a point of view, and the community as the marketing engine. The brand roster is sharp. The retail philosophy is real. The opportunity is to translate the vision into an operating plan that holds up to capital, vendors, and customers.

Three things stood out from the working notes:

- A defined assortment philosophy across snow, hike, trail, road, and water — anchored by core brands and lifted by trend-forward names like Satisfy, District Vision, Speedland, Hylo, and Mount to Coast.

- A retail model that rejects the influencer playbook in favor of athlete experts, run club integration, and a prototype-store-as-tradeshow approach.

- Real open questions about COGS, margin architecture, warehouse logistics, and what "fastest ROI" actually looks like across e-comm and physical.

This proposal is built around closing those open questions in 30 days — and giving you a defensible plan for what to build, buy, and launch first.

02 · THE APPROACH

Three pillars. One 30-day engagement.

Every option below is structured around the same three pillars surfaced in our discovery conversation — what changes between tiers is depth, deliverable scope, and how much of the execution we tackle inside the 30 days.

Pillar 01 — Assortment & brand roster

Build a defensible point of view on what SX Collective sells, why, and in what mix. Stress-test brand selection against margin, MAP integrity, and the trend-vs-core balance. Identify which brands are buy-now, which are build-toward, and which are noise.

Pillar 02 — Retail concept & community model

Translate the anti-influencer, athlete-led, run-club-anchored philosophy into a concrete store concept and activation playbook — including the prototype-store / tradeshow-to-the-public format and how it plugs into existing space.

Pillar 03 — Marketing tie-ins & fastest-ROI initiatives

Sequence the work so e-comm wins fund the physical experience. Identify the marketing-to-assortment moments that move product without spending into an advertising budget that doesn't fit the brand.

03 · ENGAGEMENT OPTIONS

Three ways to work together.

All three options run for the same 30-day window. They differ in how deep we go, how much of the execution lives inside the engagement, and how much budget you're committing on a first project together.

|  | TIER 01 | TIER 02 Recommended | TIER 03 |
| --- | --- | --- | --- |
|  | The Diagnostic | Strategic Roadmap | Roadmap + Activation |
| Investment | $8,500 | $22,000 | $38,000 |
| Duration | 30 days | 30 days | 30 days |
| Engagement style | Fixed scope, deliverable-based | Fixed scope, deliverable-based | Fixed scope, deliverable-based |
| Best for | You want a sharp outside read before committing capital. | You want a strategic plan you can execute against for the next 6–12 months. | You want strategy and a running start on Pillar 01 inside the same 30 days. |
| Working sessions | 1 kickoff + 1 readout | 1 kickoff + 2 working + 1 readout | 1 kickoff + weekly working sessions + final readout |
| Stakeholder interviews | Up to 2 | Up to 4 | Up to 6 |
| Final deliverables | Diagnostic report + prioritized opportunity list | Everything in Tier 01 + 12-month assortment & retail strategy + 30/60/90 plan | Everything in Tier 02 + first 90-day buy plan + store concept brief + activation playbook |

Tier 02 is the recommended starting point for a brand at SX Collective's stage — it produces a complete operating plan you can hand to investors, vendors, or a future hire, without the larger investment of the activation tier.

04 · WHAT'S INCLUDED

Scope by tier.

Tier 01 — The Diagnostic

$8,500  ·  30-day engagement  ·  Fixed-scope deliverables

A focused outside read on the work in flight. The deliverable is a written diagnostic plus a prioritized list of opportunities ranked by speed to revenue.

- Review of current assortment, brand roster, MAP policy direction, and trend-brand mix

- Up to 2 stakeholder interviews (founder + one operator)

- Competitive scan of 4–6 adjacent retail concepts (specialty run, outdoor, lifestyle)

- Margin and unit-economics gut-check on 3–5 representative SKUs

- Written diagnostic with findings, risks, and ranked opportunity list

Tier 02 — Strategic Roadmap

$22,000  ·  30-day engagement  ·  Fixed-scope deliverables  ·  RECOMMENDED

Everything in The Diagnostic, plus a complete strategic operating plan across all three pillars. The output is a plan you can execute against for the next 6–12 months.

- Everything included in Tier 01

- 12-month assortment strategy with brand roster framework — Build / Maintain / Test / Exit

- MAP policy recommendations and pricing architecture

- Retail concept positioning document — community model, store format, activation strategy

- Marketing-to-assortment tie-in framework (no paid media required)

- 30 / 60 / 90 day execution plan with owners and decision points

Tier 03 — Roadmap + Activation

$38,000  ·  30-day engagement  ·  Fixed-scope deliverables

Everything in the Strategic Roadmap, plus the first 30 days of execution on Pillar 01. You leave the engagement with a plan and a running start.

- Everything included in Tier 02

- Vendor outreach and brand onboarding prep for top 5 trend-opportunity brands (Satisfy, District Vision, Speedland, Hylo, Mount to Coast)

- Initial 90-day buy plan with unit economics and margin sensitivity

- Store concept brief sized to hand to a designer or general contractor

- Run club / community activation playbook with a 90-day calendar

05 · TIMELINE

The 30-day arc.

Same shape across all three tiers — the depth of each phase scales with the option you select.

| WEEK | PHASE | WHAT HAPPENS |
| --- | --- | --- |
| Week 01 | Discovery & alignment | Kickoff. Stakeholder interviews. Document review (current brand roster, financials, store thinking). Confirm success metrics and decision rights for the engagement. |
| Week 02 | Diagnosis & framing | Assortment audit, competitive scan, margin gut-check. First working session to align on what we're seeing before we commit to recommendations. |
| Week 03 | Build the plan | Synthesize findings into the assortment framework, retail concept, and ROI sequencing. Second working session to pressure-test the strategy with you. |
| Week 04 | Land the plan | Final deliverables packaged. Tier 03: vendor outreach in flight, buy plan finalized, store brief delivered. |

You'll know by the end of Week 02 whether the strategy is going to land — that's the working session designed to surface disagreement before we commit anything to deliverables.

06 · INVESTMENT & TERMS

The commercials.

Pricing is fixed-fee per tier. No hourly billing, no surprise invoices.

| Payment structure | 50% upon signed engagement letter. 50% on final SOP deliverables.. |
| --- | --- |
| Scheduling | Work is delivered against the dates below. How time is allocated within the 30-day window is at the consultant's discretion. Responsive within one business day during the engagement. |
| Expenses | Travel and out-of-pocket expenses billed at cost with prior approval. |
| Out-of-scope work | Anything outside the agreed pillars is quoted separately at $250/hr or as a fixed-fee add-on, your choice. |
| Confidentiality | Mutual NDA executed before kickoff. All work product is yours. |
| Cancellation | Either party may exit with 7 days written notice. Fees pro-rated to work completed. |
| Start date | Within 10 business days of countersignature. |

07 · ABOUT

The Strategy Studio.

The Strategy Studio is a boutique consultancy for consumer brands and retailers at growth inflection points. We work with founders and operating teams who don't need another deck — they need someone who has actually been the buyer, run the negotiation, owned the margin, and made the call.

Strategy that holds. Where rigor meets range.

Why Addie

- 10+ years in retail buying, merchandising, and operations across outdoor, specialty, beauty, and lifestyle

- Senior Buyer at Backcountry — managed footwear category across Nike, Adidas Terrex, Merrell, Salomon, Norda, Brooks, and others

- Director of Purchasing at New World Natural Brands — built operational processes across multiple brands

- Operator first, consultant second — every recommendation has been carried out under a real P&L before it ends up in a deliverable

08 · NEXT STEPS

How we move.

Three things between this proposal and a kickoff:

- Pick a tier — or tell me what you'd want to flex. Tier 02 is the recommended starting point.

- Sign the engagement letter and mutual NDA (I'll send both post tier selection).

- Confirm a kickoff date and define goals and success metrics Week 01.

A NOTE ON FIRST PROJECTS

This is the kind of work I built The Strategy Studio for. As with any new business, there are dependencies — vendor responsiveness, internal data access, scheduling — that can occasionally shift a deliverable date by a few days. Where that happens, I'll surface it early, agree on the fix with you, and never let it move the final readout date without explicit sign-off.