COMPANION DOCUMENT  ·  WORKING DOCUMENT

Prepared for SX Collective

Project Timeline & Scope

This document accompanies the signed engagement letter and covers the weekly phases, working session cadence, deliverable milestones, and dependencies for the 30-day project. Dates are anchored to the confirmed kickoff, and the document is updated together during the engagement if inputs, data, or priorities change.

Important. This is a working document, not a contract. It is illustrative of the work produced during the engagement and evolves as Consultant and Client learn more together. Specific formats, granularity, quantities, SKUs, brands, timelines, and metrics referenced in this document are subject to change based on the data available, stakeholder input, and priorities that emerge during the engagement. This document does not modify or expand the commercial terms in the signed proposal or the Master Services Agreement. Neither party is legally bound to any specific content, format, quantity, or outcome described here. The proposal and the signed engagement letter govern the engagement; this document supports it.

Confirmed kickoff date	Week of  ____________________

Final readout date	30 days from kickoff

Selected tier	____________________________________

01 · Engagement Shape

The 30-day arc.

The engagement moves through four weekly phases, with structured working sessions built in to test thinking against the data before it becomes a deliverable. The phase structure is the same across tiers. Depth and output scale with the tier selected in the signed engagement letter.

Workflow at a glance

Phases shown by week. Calendar dates are confirmed at engagement-letter signature.

| Phase | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Readout |
| --- | --- | --- | --- | --- | --- |
| Kickoff |  |  |  |  |  |
| Discovery |  |  |  |  |  |
| Diagnosis |  |  |  |  |  |
| Build the plan |  |  |  |  |  |
| Working sessions |  |  |  |  |  |
| Final deliverables |  |  |  |  |  |
| Executive readout |  |  |  |  |  |

Light bars mark active work. Black bars mark the kickoff and the final readout milestones.

Weekly phases

| Week | Phase | What happens |
| --- | --- | --- |
| Week 01 | Discovery & alignment | Kickoff call. Stakeholder interviews. Document review of current brand roster, financials, and any existing store/concept thinking. Confirm success metrics and decision rights for the engagement. |
| Week 02 | Diagnosis & framing | Assortment audit, competitive scan of adjacent retail concepts, margin and unit-economics review on representative SKUs. Working Session 1 with the client to align on findings before any recommendations are committed. |
| Week 03 | Build the plan | Pull findings together into the assortment framework (all tiers). Tier 03 also develops the retail concept positioning and the marketing-to-assortment tie-in framework. Working Session 2 to check the strategy with the client (Tiers 02 and 03). |
| Week 04 | Land the plan | Final deliverables packaged. Executive readout delivered. Client review window opens on deliverable delivery and closes five business days later per Deliverable Acceptance terms. |

Working session cadence

Working sessions are 60 to 75 minute calls designed to land decisions, not just have a discussion. Each one has a pre-read sent 24 hours ahead and a short decisions-and-open-questions summary sent within 24 hours after.

- Kickoff. Week 01. 60 to 75 min. Success metrics, decision rights, data-access checklist, stakeholder interview schedule. All tiers.

- Working Session 1. Week 02. 60 min. Diagnosis and findings alignment. All tiers.

- Working Session 2. Week 03. 60 min. Strategy framework review. Tiers 02 and 03.

- Working Session 3. Week 03. 60 min. Retail concept and marketing frameworks review. Tier 03 only.

- Final pre-read. Week 04. 30 min. Walk-through of the final-deliverable draft before the executive readout, to surface any last adjustments. Tiers 02 and 03.

- Executive readout. Week 04. 60 to 90 min. Final deliverable walkthrough, decisions captured, next-steps framing. All tiers.

02 · Deliverable Milestones

What lands when.

Milestones are anchored to the confirmed kickoff date. Day numbers are relative to kickoff (Day 1). Calendar dates populate once the kickoff date is confirmed at engagement-letter signature.

| Day | Date | Milestone | Applies to |
| --- | --- | --- | --- |
| Day -7 | __________ | Engagement letter and NDA countersigned. Deposit invoice issued. | All tiers |
| Day -3 | __________ | Pre-read sent. Data access checklist shared. | All tiers |
| Day 1 | __________ | Kickoff call. Success metrics and decision rights confirmed. | All tiers |
| Day 5 | __________ | Stakeholder interviews complete. Document review wrapped. | All tiers |
| Day 10 | __________ | Working Session 1. Diagnosis and findings alignment. | All tiers |
| Day 12 | __________ | Diagnostic findings draft delivered for review. | All tiers |
| Day 17 | __________ | Working Session 2. Strategy framework review. | Tiers 02 + 03 |
| Day 19 | __________ | Working Session 3. Retail concept and marketing review. | Tier 03 only |
| Day 21 | __________ | Strategic plan draft delivered. Client review window opens. | Tiers 02 + 03 |
| Day 24 | __________ | 30-min final-deliverables pre-read call. | Tiers 02 + 03 |
| Day 26 | __________ | Client review window closes. Final revisions incorporated. | All tiers |
| Day 28 | __________ | Final readout. Deliverables delivered. Final invoice issued. | All tiers |

Milestones are the operating rhythm. Any change to a delivery date is flagged in writing at least five business days in advance and agreed collaboratively.

03 · Scope by Tier

What the deliverables actually contain.

This section expands the deliverables listed in the proposal. It describes the specific contents and scope of each output so both parties are aligned on what the work actually looks like. This document is the operational reference, not a contract.

Tier 01: The Diagnostic

- Review of current assortment, brand roster, and MAP policy direction. Intended to flag gaps, overlaps, and consolidation candidates at roughly the SKU or product-group level.

- Margin and unit-economics review of the assortment. Typically covers 3 to 5 representative SKUs with flagged pricing or brand-mix anomalies and directional margin impact of each.

- Competitive scan of 3 to 4 adjacent retail concepts across specialty run, outdoor, and lifestyle. Output is a short positioning view showing where SX sits relative to each.

- Ranked opportunity list, usually 5 to 7 items, prioritized by speed to revenue or margin, with a directional impact estimate (in dollars, points, or percent as appropriate) and a rough read on effort to execute.

- Written diagnostic document with findings, risks, and the ranked list. Underlying analysis is shared as a companion spreadsheet.

- Up to 3 stakeholder interviews.

- 60-minute executive readout with findings walk-through and decisions captured.

- Up to 3 rounds of revision on the written diagnostic.

Tier 02: The Assortment Plan

- Everything in Tier 01.

- 12-month assortment plan. Intended to include SKU-level or category-level targets, brand allocation percentages by category, and margin targets by category. Final format and granularity are agreed together during the engagement based on the data available.

- Brand roster framework using Build / Maintain / Test / Exit categories, with brand assignments and the reasoning behind each placement.

- MAP policy and pricing recommendations covering pricing floors, promo windows, and enforcement triggers at the SKU or category level.

- Directional notes on retail concept (Pillar 02) and marketing tie-ins (Pillar 03). Usually 2 to 3 next-step recommendations for each. Not full plans at this tier.

- 30 / 60 / 90 day execution plan focused on Pillar 01, with owners, decision points, and target revenue or margin outcomes at each milestone.

- Up to 5 stakeholder interviews.

- 2 mid-engagement working sessions, a 30-minute final-deliverables pre-read in Week 04, and a final readout deck.

- Up to 3 rounds of revision on each deliverable.

Tier 03: The Full Plan

- Everything in Tier 02.

- Retail concept positioning document. Intended to cover community model specifics, store format requirements (size, layout, fixture types, and prototype-store or sample-sale mechanics), and an activation calendar tied to run club events and athlete moments.

- Marketing-to-assortment tie-in framework. Usually includes 3 to 5 campaign concepts tied to product drops or run club events, each with target audience, channel mix, and a success metric. Built to work without paid media, with the option to layer paid media on top if chosen.

- Content and events calendar (roughly 90 days) connecting drops to the underlying assortment.

- Vendor outreach starter list for 3 to 5 trend-opportunity brands (Satisfy, District Vision, Speedland, Hylo, Mount to Coast, or others agreed at kickoff), including named vendor contacts where available, a suggested opening pitch, and negotiation talking points for MAP and exclusivity.

- 30 / 60 / 90 day execution plan across all three pillars, with owners, decision points, and target revenue or margin outcomes at each milestone.

- Up to 7 stakeholder interviews.

- 3 mid-engagement working sessions, a 30-minute final-deliverables pre-read in Week 04, and a final readout deck.

- Up to 3 rounds of revision on each deliverable.

Final format, granularity, and exact contents of each deliverable are agreed together during the engagement and reflected in this document, not in the proposal. The goal is to match the depth of the output to the depth of the data available and the decisions the work needs to support.

04 · Dependencies & Inputs

What keeps the plan on track.

The timeline above assumes the following inputs and access are provided by the client on the schedule indicated. Delays on any of these shift downstream milestones. See the Stop-work clause in the proposal terms.

From the client, by end of Week 01

- A single point of contact for scheduling, introductions, and data access

- Read-only access to current assortment data (SKU list, cost, sell-through, inventory on hand)

- Current P&L or unit-economics reference (rough is acceptable) to support the margin and unit-economics review

- Intros to the 2–5 internal stakeholders identified at kickoff

- Any existing brand, concept, or investor documents that describe the SX Collective vision

Ongoing, throughout the engagement

- Feedback on drafts within 3 business days of delivery

- Availability for the scheduled working sessions (1 / 2 / 3 mid-engagement sessions depending on tier, plus final pre-read for Tiers 02 and 03)

- A decision-maker available within 24 hours for escalations on scope or direction

From the consultant

- Responsiveness within one business day during the engagement

- Written check-ins at key milestones summarizing progress, open questions, and what's needed from the client next. Cadence is set at kickoff, not fixed to a weekly calendar.

- Pre-reads delivered 24 hours before every working session

- Decisions-and-open-questions summary within 24 hours of every working session

Changes to this document are captured in a short change log appended on the final page at the close of the engagement. Both parties reference this document, together with the signed engagement letter, as the working scope of the project.

THE STRATEGY STUDIO

Strategy that holds.  ·  Where rigor meets range.